## project GRAPH
CUSTOMER/BUSINESS
LOGIN/REGISTER
CUSTOMER
BUSINESS
UPLOAD OR EDIT PRODUCTS
SEARCH
FOR COMPETITION
MAPS
PROGRAMS NEEDED
1.ANDROID STUDIO
2.GITHUB DESKTOP
3.EXCEL 2008 OR LATER
4.Xammp

## TASKS
weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
days | 25-Oct | 01-Nov | 08-Nov | 15-Nov | 22-Nov | 29-Nov | 06-Dec | 13-Dec | 20-Dec | FINAL
Θεόφιλος | GITHUB ACOUNT/AND TEST PUSH/FETCH | ORGANISE GITHUB &DATABASE RESEARCH | DATABASE CREATION(OKEANOS) | DATABASE &MAIN FORM CREATION | MAIN FORM TESTING | FINAL FORM FIX AND TESTING | PROBLEM SOLVE WITHDATABASE | FINAL CHANGES | PRODUCT SHOWCASE
Κώστας | GITHUB ACOUNT/AND TEST PUSH/FETCH | LOGIN FORM RESEARCH | LOGIN FORM CREATION | LOGIN FORM CREATION | CONNECT LOGIN TO MAIN | FINAL FORM FIX AND TESTING | PROBLEM SOLVE WITHDATABASE | FINAL CHANGES | PRODUCT SHOWCASE
Δημήτρης | GITHUB ACOUNT/AND TEST PUSH/FETCH | USER FORM RESEARCH | USER FORM CREATION | USER FORM CREATION | CONNECT USER TO MAIN | DATABASE RESEACH FOR HELP | REARCH HELP FOR DATABASE | CUSTOMISE DESIGN | PRODUCT SHOWCASE
ΒαγγέληςΒ | GITHUB ACOUNT/AND TEST PUSH/FETCH | REGISTER FORM RESEARCH | REGISTER FORM CREATION | REGISTER FORM CREATION | CONNECT REGISTER TO MAIN | DATABASE RESEACH FOR HELP | REARCH HELP FOR DATABASE | CUSTOMISE DESIGN | PRODUCT SHOWCASE
Βαγγέλης 4016 | GITHUB ACOUNT/AND TEST PUSH/FETCH | CUSTOMER FORM RESEARCH | CUSTOMER FORM CREATION | CUSTOMER FORM CREATION | CONNECT CUSTOMER TO MAIN | FINAL FORM FIX AND TESTING | REARCH HELP FOR DATABASE | ADD PRODUCTS TO DATABASE | PRODUCT SHOWCASE
Γιώργος | GITHUB ACOUNT/AND TEST PUSH/FETCH | TRANFERLOG &DATABASE RESEARCH | DATABASE CREATION(OKEANOS) | DATABASE CREATION(OKEANOS) | DATABASE CONNECTION TO MAIN (ERROR SOLVING) | FINAL DATABASE | TESTING FOR ALTERNATIVE DATABASE SOURCE | ADD PRODUCTS TO DATABASE | PRODUCT SHOWCASE

## NOTES
Stories | Story1 |  | Story2 |  | Story3 |  | Story4 |  | Story5 |  | Story6 |  | Story7 | Story8 | Story9 | Story10 | Story11
Tasks | CreateDataBase |  | Login |  | Register |  | TransferLog |  | UserForm |  | ShopKeeperForm
1 | Testing Push & Fetch | 2017-10-22 | Testing Push and Fetch | 2017-10-22 | Push and Fetch Testing | 2017-10-22 | Testing Push & Fetch | 2017-10-22 | Testing github push and fetch | 2017-10-25 | Testing github push and fetch | 2017-10-24
2 | Organizing Github | 2017-10-23 | youtube research on Login form creation | 2017-10-23 | Learn Android Studio form creation | 2017-11-01 | Learn Android Studio form creation | 2017-10-23 | Testing github push and fetch to solve connectivity | 2017-10-26 | make Shopkeeper project | 2017-10-25
3 | Team Task assignment | 2017-11-01 | github Form research | 2017-10-24 | researth Register Form how to | 2017-11-02 | github Form research | 2017-10-24 | researching Google about android Studio | 2017-10-27 | desing shopkeeper form | 2017-10-29
4 | Αίτηση στον ωκεανο | 2017-11-08 | 1st Login Version Complete | 2017-11-01 | 1st Register version Complete | 2017-11-03 | Tranferlog complete | 2017-11-01 | Github search about userforms | 2017-11-03 | write code for applications buttons | 2017-11-01
5 | XAMPP | 2017-11-09 | anding Facebook conect to login | 2017-11-02 | ading Facebook Register to register form | 2017-11-08 | pushing to main | 2017-11-08 | Starting Userform | 2017-11-04 | completing the first version | 2017-11-08
6 | PhpMyAdmin | 2017-11-15 | Ασχοληθηκα με τα layouts της εφαρμογης | 2017-11-09 | Find youtube video advices about merging forms | 2017-11-15 | rebuilding Database to okeanos | 2017-11-22 | Completing Userform | 2017-11-08 | pushing to master | 2017-11-22
7 | MySqlDatabase | 2017-11-16 | Ερευνα και χρήση googlemaps | 2017-11-10 | Write code for the background color of the application | 2017-11-23 | fixing database with the help of youtube research | 2017-11-29 | researching on how to merge forms | 2017-11-09 | learn on youtube how to merge layout in android studio | 2017-11-23
8 | Main form complete | 2017-11-28 | merging with main | 2017-11-11 | Write code for he vision of the password edit text | 2017-11-24 | connecting Database with main | 2017-12-01 | merging to main | 2017-11-16 | importing new setting | 2017-11-29
9 | Main form testing(with other forms added | 2017-11-29 | helping with tweeks | 2017-11-29 | connecting register with main form | 2017-11-29 | connecting tranferlog with main | 2017-12-02 | merging to main the updated userform version | 2017-11-28 | write the code to merge the programs | 2017-11-30
10 | Final form tweeking | 2017-11-30 | helping with database connectivity | 2017-12-01 | reconecting fixed form | 2017-11-30 | helping with database connectivity | 2017-12-03 | Alternative search for other databases | 2017-11-29 | merge complete | 2017-12-01
11 | Solving database problem | 2017-12-01 | tweeking Stories Excell | 2017-12-06 | RESEARCHING about database conectivity | 2017-12-04 | solving Conectivity Problems | 2017-12-04 | merge complete | 2017-12-01 | help with server conectivity | 2017-12-06
12 | research about database errors | 2017-12-06 |  |  | 1stdatabase connection attempt | 2017-12-06 |  |  | help with server conectivity | 2017-12-06
13 | sovled 2/5 problems | 2017-12-06